## updated Feature Listing
User Panel ( Android & iOS App ) | [6 empty] | Client Communication |  | MAN Hours
S.No. | Phase | Sprint | Module | Functionality | API | Client Dependency | Client Response | Fluper Response | UI/UX Design | Android Efforts | iOS Efforts | Q/C Testing | Project Management | Total Efforts
1 | Splash Screen
2 | Registration | New Registration | Sign In | User will Sign Up with the Following details(All fields are mandatory): 1. Mobile Number/Email ID 2. Choose Password 3. Confirm Password * User will receive a confirmation mail once his account gets successfully created. | Not Applicable
|  | Verification |  | User will verify his Email Id/Mobile Number, he will receive an OTP after entering the OTP , Mobile Number will get Verified. For email , a mail will be sent to user's entered email which he will have to open and follow the link. | Third Party API Integration ex: Twilio
|  | Already Registered | Sign In | User will Sign In with the Following details: 1. Mobile Number/Email ID 2. Password | Not Applicable
|  | Password Recovery |  | User will Reset his password through his Mobile Number/Email ID, he' ll get an OTP on his Mobile Number which he has entered at the Time of Sign In. After entering the OTP, he will be able to Reset his Password. Or he would receive a password reset link on his email. | Third Party API required; i.e; Twilio
3 | Search |  | Enter details | The user will have to enter the following details for searching the diamonds : 1. Select Stone 2. Select Price Range 3. Carat 4. Shape 5. Cut 6. Clarity 7. Color 8. Grading (Max 100) 9. Overall Score (Max 25) 10. BIA Info Code User can also reset the form. | Not Applicable
|  |  | View Search results | The user can view the search results. ( List view ) | Not Applicable
|  |  | Select Product | The user can select any product to view its details. User can view the following details: 1. Select Stone 2. Select Price Range 3. Carat 4. Shape 5. Cut 6. Clarity 7. Color 8. Grading (Max 100) 9. Overall Score (Max 25) 10. BIA Info Code 11. Share product ( Facebook, Whatsapp, email etc ) 12. Quantity 13. Buy a) The user can email the admin for placing the order. b) The user can call for placing order. (device dial up calling ) | Not Applicable
4 | Payments |  |  | The user can make online payment to buy products. User will be re-directed to a third party website for making online payments. He can pay by one of the following methods: 1. Netbanking 2. Credit card 3. Debit card | Third Party API Integration ex: PayPal
5 | Options |  | Price calculator | The user can calculate the price of the diamond. He will have to fill the following details for calculating the price : 1. Select Stone 2. Select Price Range 3. Carat 4. Shape 5. Cut 6. Clarity 7. Color 8. Grading (Max 100) 9. Overall Score (Max 25) 10. BIA Info Code | Not Applicable
|  |  | Education | The user can read about the following topics: 1. Diamond 2. Blue Gems 3. Carat 4. Clarity 5. Color 6.Cut 7. Shape 8. BIA Info Code | Not Applicable
|  |  | Delivery Address | User can manage his delivery address. He will have to provide the following details: 1. House Number 2. Street 3. City 4. State 5. Postal code 6. Country 7. Mobile Number | Not Applicable
|  |  | My Orders | User can view the status of his order . User can also cancel his order. He can view the following : 1. Current order status 2. Order History 3. Cancelled orders 4. Track order status | Not Applicable
|  |  | Notifications | User will receive notifications from the Admin. User will also receive promotional notifications from admin. | Not Applicable
|  |  | About Us | User can read the about us of the app. | Not Applicable
|  |  | Contact Us | User can view the contact details. | Not Applicable
|  |  | Send Email | User can send an email to the admin | Not Applicable
|  |  | Website | The user can go directly to product page | Not Applicable
Admin Panel( Website ) | [6 empty] | Client Communication |  | MAN Hours
S.No. | Phase | Sprint | Module | Functionality | API | Client Dependency | Client Response | Fluper Response | UI/UX Design | Android Efforts | iOS Efforts | Q/C Testing | Project Management | Total Efforts
1 | Registration | Sign In |  | Admin will sign in with following details : 1. Email 2. Password * Details will be provided by us | Not Applicable
|  | Forgot Password |  | * Admin can reset his password by clicking on forgot password link. A password reset link will be sent to his registered Email address. | Not Applicable
2 | Account Management |  | View | * Admin can view all of its total users registered | Not Applicable
|  |  | Remove | * Admin can remove users * Admin can block users | Not Applicable
| Orders |  |  | Admin can view the following : 1. Current orders 2. Order history 3.track order | Not Applicable
3 | Report Generations |  |  | *Admin will generate report on 1.Daily Basis 2.Weekly Basis 3.Monthly Basis Admin will generate reports in different formats | Not Applicable
4 | Products |  | Add/delete | * Admin will add/delete Products with the following details : 1. Select Stone 2. Select Price Range 3. Carat 4. Shape 5. Cut 6. Clarity 7. Color 8. Grading (Max 100) 9. Overall Score (Max 25) 10. BIA Info Code | Not Applicable
5 | Payments |  |  | Admin can view the received payments | Third Party API Integration ex: PayPal
6 | Notifications |  |  | *The Admin can send notifications. * Admin can see email notifications from user. * Admin can send promotional notifications to the user. | Not Applicable
7 | Settings |  | Edit Details | * Admin will update terms and conditions. * Admin will update About us of app * Admin will update privacy policy of the app * Admin will update FAQs and Education articles. | Not Applicable
|  |  | Account Settings | Admin can log out of the app. Admin can change the password of the app. | Not Applicable